## Deliverables Mapping
AI_Powered_Model — Deliverables Mapping
Mapped to the actual repo folder structure (client / server / ml_engine)
Legend: Yellow cells (Owned By, Status) are for the team to fill in. One example row is shown in row 6.
# | Module | Sub-Folder | File / Task | Task Description | Owned By | Status | Deadline
1 | Frontend (client) | public | index.html | Base HTML shell for the React app
2 | Frontend (client) | charts | CategoryChart.jsx | Chart showing issues broken down by category
3 |  | charts | MissingChart.jsx | Chart visualizing missing-value distribution
4 |  | charts | OutlierChart.jsx | Chart visualizing outlier/anomaly distribution
5 |  | charts | QualityChart.jsx | Quality score gauge/trend chart
6 | Frontend (client) | components | ChartCard.jsx | Reusable card wrapper for chart components
7 |  | components | DataTable.jsx | Filterable/sortable table for flagged issues
8 |  | components | Loader.jsx | Loading spinner shown during pipeline runs
9 |  | components | MetricCard.jsx | Headline metric card (score, rows, issues, critical count)
10 |  | components | Navbar.jsx | Top navigation bar
11 |  | components | SeverityBadge.jsx | Color-coded severity badge (high/medium/low)
12 |  | components | Sidebar.jsx | Side navigation / detectors list panel
13 |  | components | UploadBox.jsx | Drag-and-drop CSV/Excel upload component
14 | Frontend (client) | pages | Home.jsx | Landing page
15 |  | pages | Upload.jsx | Dataset upload screen
16 |  | pages | Dashboard.jsx | Overview dashboard (score cards, gauge)
17 |  | pages | Validation.jsx | Validation results screen with filters
18 |  | pages | Anomaly.jsx | Anomaly & outlier visualization screen
19 |  | pages | Quality.jsx | Quality scoring breakdown screen
20 |  | pages | AIExplanation.jsx | AI-generated summary panel
21 |  | pages | Reports.jsx | Reports & export download screen
22 | Frontend (client) | services | api.js | Base Axios instance / API client config
23 |  | services | uploadApi.js | API calls for dataset upload
24 |  | services | reportApi.js | API calls for report generation/downloads
25 | Frontend (client) | app setup | App.jsx | Root component + routing
26 |  | app setup | main.jsx | React app entry point
27 |  | app setup | index.css | Global styles
28 |  | app setup | package.json / vite.config.js | Project dependencies and Vite build config
29 | Backend (server) | config | db.js | MongoDB connection setup
30 |  | config | multer.js | File upload middleware config
31 | Backend (server) | controllers | uploadController.js | Handle dataset upload requests
32 |  | controllers | validationController.js | Trigger validation pipeline, return results
33 |  | controllers | reportController.js | Generate and serve report downloads
34 |  | controllers | dashboardController.js | Aggregate data for dashboard endpoints
35 | Backend (server) | routes | uploadRoutes.js | POST /api/upload route
36 |  | routes | validationRoutes.js | POST /api/validate route
37 |  | routes | reportRoutes.js | POST /api/report, GET /api/report/:id routes
38 |  | routes | dashboardRoutes.js | GET /api/dashboard route
39 | Backend (server) | middleware | errorHandler.js | Centralized error handling middleware
40 | Backend (server) | models | User.js | User schema
41 |  | models | Dataset.js | Uploaded dataset schema
42 |  | models | Report.js | Generated report schema
43 |  | models | Anomaly.js | Anomaly/flagged-issue log schema
44 | Backend (server) | services | pythonService.js | Bridge to call the Python ml_engine pipeline
45 |  | services | reportService.js | Report file generation/storage logic
46 | Backend (server) | app setup | app.js / server.js | Express app setup and server entry point
47 |  | app setup | package.json | Backend dependencies
48 | ML Engine (ml_engine) | notebooks | validation.ipynb | Null/duplicate/datatype/date/quantity/price/payment/product/status/regex checks — all in one | Shyamal Rai | Done | 14-08-2026
49 |  | notebooks | cleaning.ipynb | Missing-value handling, date repair, payment/product standardization, price parsing | Shyamal Rai | Done | 14-08-2026
50 |  | notebooks | rules.ipynb | Business rule engine — negative qty/price, invalid dates, duplicate IDs, unrecognized categories | Shyamal Rai | Done | 14-08-2026
51 |  | notebooks | statistics.ipynb | Z-score and IQR statistical outlier detection | Shyamal Rai | Done | 14-08-2026
52 |  | notebooks | anomaly.ipynb | Isolation Forest, Local Outlier Factor, DBSCAN — all in one | Shyamal Rai | Done | 14-08-2026
53 |  | notebooks | scoring.ipynb | Dataset score, record score, completeness score | Shyamal Rai | Done | 14-08-2026
54 |  | notebooks | ai_explanation.ipynb | LLM-generated plain-English summaries and recommendations | Shyamal Rai | Done | 14-08-2026
55 |  | notebooks | reports.ipynb | PDF, Excel, and PPT report generation | Shyamal Rai | Done | 14-08-2026
56 |  | notebooks | run_pipeline.ipynb | Orchestrates all notebooks/stages end to end | Shyamal Rai | Done | 14-08-2026
57 | ML Engine (ml_engine) | data & models | data/dataset_ecommerce_transactions_data.csv | Sample dataset for development/testing | Shyamal Rai | Done | 14-08-2026
58 |  | data & models | models/ | Saved ML model files (Isolation Forest, DBSCAN, etc.) | Shyamal Rai | Done | 14-08-2026
59 |  | data & models | requirements.txt | Python dependencies for ml_engine | Shyamal Rai | Done | 14-08-2026
60 | Project Setup | docs | new_project_structure.pdf / project_structure.pdf | Reference architecture docs | Shyamal Rai | Done | 14-08-2026
61 | Project Setup | root | reports/ | Output folder for generated reports | Shyamal Rai | Done | 14-08-2026
62 |  | root | uploads/ | Runtime storage for uploaded datasets | Shyamal Rai | Done | 14-08-2026
63 |  | root | README.md | Setup and run instructions | Shyamal Rai | Done | 14-08-2026
64 |  | root | docker-compose.yml | Container orchestration for client + server + ml_engine | Shyamal Rai | Done | 14-08-2026
65 |  | root | .gitignore | Excludes node_modules, .venv, uploads, checkpoints, etc. | Shyamal Rai | Done | 14-08-2026

## Summary
Work Division Summary
Auto-calculated from the Deliverables Mapping sheet.
Tasks by Owner
Owner | Task Count
Shyamal Rai | 0
Kartikeya Gupta | 0
Lakshay Garg | 0
Tasks by Module
Module | Task Count
Frontend (client) | 6
Backend (server) | 7
ML Engine (ml_engine) | 2
Project Setup | 2
Tasks by Status
Status | Task Count
Not Started | 0
In Progress | 0
Blocked | 0
Done | 18
Total Tasks | 65